## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
0 | Yes | Auto Scheduled | AWS to GCP Migration | 540 hrs? | 2021 May 03 8:00 AM | 2021 August 04 12:00 PM |  | 0
1 | Yes | Auto Scheduled | Scope | 36 hrs | 2021 May 03 8:00 AM | 2021 May 07 12:00 PM |  | 1
2 | Yes | Auto Scheduled | Conduct needs analysis | 4 hrs | 2021 May 03 8:00 AM | 2021 May 03 12:00 PM |  | 2
3 | Yes | Auto Scheduled | Identify stakeholder needs, influence on project | 4 hrs | 2021 May 03 8:00 AM | 2021 May 03 12:00 PM |  | 2
4 | Yes | Auto Scheduled | Determine project scope | 2 hrs | 2021 May 04 8:00 AM | 2021 May 04 10:00 AM |  | 2
5 | Yes | Auto Scheduled | Develop a proposal | 4 hrs | 2021 May 04 10:00 AM | 2021 May 04 3:00 PM | 4 | 2
6 | Yes | Auto Scheduled | Define preliminary resources | 2 hrs | 2021 May 05 8:00 AM | 2021 May 05 10:00 AM |  | 2
7 | Yes | Auto Scheduled | Secure project sponsorship | 1 hr | 2021 May 06 8:00 AM | 2021 May 06 9:00 AM | 5,6 | 2
8 | Yes | Auto Scheduled | Secure core resources | 4 hrs | 2021 May 07 8:00 AM | 2021 May 07 12:00 PM | 7 | 2
9 | Yes | Auto Scheduled | Scope complete | 0 days | 2021 May 07 8:00 AM | 2021 May 07 8:00 AM | 7 | 2
10 | Yes | Manually Scheduled | Concept | 64 hrs? | 2021 May 10 8:00 AM | 2021 May 19 5:00 PM |  | 1
11 | Yes | Auto Scheduled | Identify security and compliance requirements | 2 hrs | 2021 May 10 8:00 AM | 2021 May 10 10:00 AM |  | 2
12 | Yes | Auto Scheduled | Create governance workbook | 3 hrs | 2021 May 10 8:00 AM | 2021 May 10 11:00 AM |  | 2
13 | Yes | Manually Scheduled | Draft preliminary architecture specifications | 16 hrs? | 2021 May 11 8:00 AM | 2021 May 12 5:00 PM |  | 2
14 | Yes | Auto Scheduled | Identify all the application environments | 2 hrs | 2021 May 11 8:00 AM | 2021 May 11 10:00 AM |  | 3
15 | Yes | Auto Scheduled | Perform application walkthroughs | 1 hr | 2021 May 11 8:00 AM | 2021 May 11 9:00 AM |  | 3
16 | Yes | Auto Scheduled | Establish pre-migration performance baseline in AWS CloudWatch dashboard | 4 hrs | 2021 May 11 8:00 AM | 2021 May 11 12:00 PM |  | 3
17 | Yes | Auto Scheduled | Determine options for google cloud services | 5 hrs | 2021 May 12 8:00 AM | 2021 May 12 2:00 PM |  | 3
18 | Yes | Auto Scheduled | Identify application integration requirements | 3 hrs | 2021 May 12 8:00 AM | 2021 May 12 11:00 AM |  | 3
19 | Yes | Manually Scheduled | Define Migration Approach | 16 hrs | 2021 May 13 8:00 AM | 2021 May 14 5:00 PM |  | 2
20 | Yes | Auto Scheduled | Perform deployment assessment | 3 hrs | 2021 May 13 8:00 AM | 2021 May 13 11:00 AM |  | 3
21 | Yes | Auto Scheduled | Identify data that does not require migration - purge/archive based on retention policies | 3 hrs | 2021 May 13 8:00 AM | 2021 May 13 11:00 AM |  | 3
22 | Yes | Auto Scheduled | Identify data that requires cleanup for integrity | 2 hrs | 2021 May 13 8:00 AM | 2021 May 13 10:00 AM |  | 3
23 | Yes | Auto Scheduled | Define migration phases | 3 hrs | 2021 May 14 8:00 AM | 2021 May 14 11:00 AM |  | 3
24 | Yes | Auto Scheduled | Define data migration approach | 3 hrs | 2021 May 14 8:00 AM | 2021 May 14 11:00 AM |  | 3
25 | Yes | Auto Scheduled | Identify production cutover window | 1 hr | 2021 May 14 8:00 AM | 2021 May 14 9:00 AM |  | 3
26 | Yes | Auto Scheduled | Perform cost benefit analysis | 4 hrs | 2021 May 17 8:00 AM | 2021 May 17 12:00 PM |  | 2
27 | Yes | Auto Scheduled | Recommend an option and obtain approvals | 0.5 hrs | 2021 May 17 1:00 PM | 2021 May 17 1:30 PM | 26 | 2
28 | Yes | Auto Scheduled | Scope all deliverables, objectives, quality, cost | 4 hrs | 2021 May 18 8:00 AM | 2021 May 18 12:00 PM |  | 2
29 | Yes | Auto Scheduled | Establish organization structure | 1 hr | 2021 May 18 8:00 AM | 2021 May 18 9:00 AM |  | 2
30 | Yes | Auto Scheduled | Define progress reporting - status reports, burndown, interdependency, schedule/plan | 2 hrs | 2021 May 18 8:00 AM | 2021 May 18 10:00 AM |  | 2
31 | Yes | Auto Scheduled | Develop a project charter | 3 hrs | 2021 May 19 8:00 AM | 2021 May 19 11:00 AM | 28 | 2
32 | Yes | Manually Scheduled | Planning | 40 hrs | 2021 May 19 8:00 AM | 2021 May 25 5:00 PM | 31 | 1
33 | Yes | Manually Scheduled | Project Plan | 11 hrs | 2021 May 19 8:00 AM | 2021 May 20 11:00 AM |  | 2
34 | Yes | Auto Scheduled | Review architecture specifications/budget with team | 2 hrs | 2021 May 19 8:00 AM | 2021 May 19 10:00 AM |  | 3
35 | Yes | Auto Scheduled | Incorporate feedback on architecture specifications | 1 hr | 2021 May 19 10:00 AM | 2021 May 19 11:00 AM | 34 | 3
36 | Yes | Auto Scheduled | Define milestones and high level tasks | 1 hr | 2021 May 19 8:00 AM | 2021 May 19 9:00 AM |  | 3
37 | Yes | Auto Scheduled | Define responsibilties for team members | 1 hr | 2021 May 19 8:00 AM | 2021 May 19 9:00 AM |  | 3
38 | Yes | Auto Scheduled | Assign resources to tasks, revise schedule depending on availability | 3 hrs | 2021 May 20 8:00 AM | 2021 May 20 11:00 AM |  | 3
39 | Yes | Auto Scheduled | Develop preliminary budget | 3 hrs | 2021 May 20 8:00 AM | 2021 May 20 11:00 AM |  | 3
40 | Yes | Manually Scheduled | Delivery and mitigation plan | 16 hrs | 2021 May 21 8:00 AM | 2021 May 24 5:00 PM |  | 2
41 | Yes | Auto Scheduled | Define test plans for unit, integration and performance testing | 2 hrs | 2021 May 21 8:00 AM | 2021 May 21 10:00 AM |  | 3
42 | Yes | Auto Scheduled | Define rollout plan | 3 hrs | 2021 May 21 8:00 AM | 2021 May 21 11:00 AM |  | 3
43 | Yes | Auto Scheduled | Identify risks, probability and impact | 2 hrs | 2021 May 21 8:00 AM | 2021 May 21 10:00 AM |  | 3
44 | Yes | Auto Scheduled | Define rollback strategy | 1 hr | 2021 May 21 8:00 AM | 2021 May 21 9:00 AM |  | 3
45 | Yes | Auto Scheduled | Develop delivery timeline | 1 hr | 2021 May 24 8:00 AM | 2021 May 24 9:00 AM |  | 3
46 | Yes | Auto Scheduled | Prepare transition readiness plan | 1 hr | 2021 May 24 8:00 AM | 2021 May 24 9:00 AM |  | 3
47 | Yes | Auto Scheduled | Obtain approvals to proceed (concept, timeline, budget) | 0 hrs | 2021 May 24 9:00 AM | 2021 May 24 9:00 AM | 41,42,43,44,45 | 2
48 | Yes | Auto Scheduled | Set up recurring business meetings | 1 hr | 2021 May 24 9:00 AM | 2021 May 24 10:00 AM | 47 | 2
49 | Yes | Auto Scheduled | Secure required resources | 1 hr | 2021 May 24 8:00 AM | 2021 May 24 9:00 AM |  | 2
50 | Yes | Auto Scheduled | Planning complete | 0 days | 2021 May 24 8:00 AM | 2021 May 24 8:00 AM |  | 2
51 | Yes | Auto Scheduled | Hold Kick-Off | 2 hrs | 2021 May 31 8:00 AM | 2021 May 31 10:00 AM | 47 | 1
52 | Yes | Manually Scheduled | Design | 24 hrs | 2021 May 31 8:00 AM | 2021 June 02 5:00 PM |  | 1
53 | Yes | Auto Scheduled | Acquire access to current applications, data stores, and services | 3 hrs | 2021 May 31 8:00 AM | 2021 May 31 11:00 AM | 47 | 2
54 | Yes | Auto Scheduled | Set up a Google Cloud account, organization, and infrastructure project | 2 hrs | 2021 May 31 8:00 AM | 2021 May 31 10:00 AM |  | 2
55 | Yes | Auto Scheduled | Create cloud source repositories | 2 hrs | 2021 May 31 8:00 AM | 2021 May 31 10:00 AM |  | 2
56 | Yes | Manually Scheduled | Review preliminary architecture specifications | 16 hrs | 2021 June 01 8:00 AM | 2021 June 02 5:00 PM |  | 2
57 | Yes | Auto Scheduled | Create a prioritized inventory of the migration components | 1 hr | 2021 June 01 8:00 AM | 2021 June 01 9:00 AM |  | 3
58 | Yes | Auto Scheduled | Identify requirements for connectivity - VPN, VPC, Peering | 4 hrs | 2021 June 01 8:00 AM | 2021 June 01 12:00 PM |  | 3
59 | Yes | Auto Scheduled | Develop functional specifications | 2 hrs | 2021 June 02 8:00 AM | 2021 June 02 10:00 AM |  | 3
60 | Yes | Auto Scheduled | Review functional specifications | 1 hr | 2021 June 02 8:00 AM | 2021 June 02 9:00 AM |  | 3
61 | Yes | Auto Scheduled | Incorporate feedback into functional specifications | 1 hr | 2021 June 02 8:00 AM | 2021 June 02 9:00 AM |  | 3
62 | Yes | Auto Scheduled | Establish cloud KPIs | 2 hrs | 2021 June 02 8:00 AM | 2021 June 02 10:00 AM |  | 2
63 | Yes | Auto Scheduled | Obtain approval to proceed | 2 hrs | 2021 June 02 8:00 AM | 2021 June 02 10:00 AM |  | 2
64 | Yes | Auto Scheduled | Design complete | 0 days | 2021 June 02 8:00 AM | 2021 June 02 8:00 AM |  | 2
65 | Yes | Manually Scheduled | Development | 96 hrs? | 2021 June 03 8:00 AM | 2021 June 18 5:00 PM | 64 | 1
66 | Yes | Auto Scheduled | Review functional specifications | 2 hrs | 2021 June 03 8:00 AM | 2021 June 03 10:00 AM |  | 2
67 | Yes | Auto Scheduled | Assign development staff | 2 hrs | 2021 June 03 8:00 AM | 2021 June 03 10:00 AM | 63 | 2
68 | Yes | Manually Scheduled | Provision Dev environment | 48 hrs? | 2021 June 04 8:00 AM | 2021 June 11 5:00 PM | 67 | 2
69 | Yes | Manually Scheduled | Clone and prepare EC2 instances | 8 hrs | 2021 June 04 8:00 AM | 2021 June 04 5:00 PM |  | 3
70 | Yes | Auto Scheduled | Create images from the EC2 instances we intend to migrate | 1 hr | 2021 June 04 8:00 AM | 2021 June 04 9:00 AM |  | 4
71 | Yes | Auto Scheduled | Create cloned instances from the EC2 instances we intend to migrate | 1 hr | 2021 June 04 8:00 AM | 2021 June 04 9:00 AM |  | 4
72 | Yes | Auto Scheduled | Modify tags for identifying the cloned machines you want to migrate | 2 hrs | 2021 June 04 8:00 AM | 2021 June 04 10:00 AM |  | 4 | nginx, application servers, instance runnign mongoDB, instances running the cron based workers, and the instance running the cron schedule broker all run on EC2...
73 | Yes | Auto Scheduled | Install the Migrate for Compute Engine Linux package to reconfigure Linux VMs for Google Cloud | 2 hrs | 2021 June 04 8:00 AM | 2021 June 04 10:00 AM |  | 4
74 | Yes | Auto Scheduled | Ensure that our cloned instances are not running | 2 hrs | 2021 June 04 8:00 AM | 2021 June 04 10:00 AM |  | 4
75 | Yes | Manually Scheduled | Configure network, access, and space requirements | 16 hrs | 2021 June 07 8:00 AM | 2021 June 08 5:00 PM |  | 3
76 | Yes | Auto Scheduled | Set up a Google Cloud Virtual Private Cloud | 1 hr | 2021 June 07 8:00 AM | 2021 June 07 9:00 AM |  | 4
77 | Yes | Auto Scheduled | Set up networks, access, and firewall rules in migration environment | 1 hr | 2021 June 07 8:00 AM | 2021 June 07 9:00 AM |  | 4
78 | Yes | Auto Scheduled | Create the Migrate for Compute Engine IAM group in AWS using the Configuration for AWS CloudFormation | 1 hr | 2021 June 07 8:00 AM | 2021 June 07 9:00 AM |  | 4
79 | Yes | Auto Scheduled | Create the AWS IAM user account for Migrate for Compute Engine with programmatic access | 1 hr | 2021 June 07 8:00 AM | 2021 June 07 9:00 AM |  | 4
80 | Yes | Auto Scheduled | Download the AWS IAM user CSV with the access keys and store securely | 1 hr | 2021 June 07 8:00 AM | 2021 June 07 9:00 AM |  | 4
81 | Yes | Auto Scheduled | Create Google Cloud roles and service accounts via Cloud Shell | 2 hrs | 2021 June 07 8:00 AM | 2021 June 07 10:00 AM |  | 4
82 | Yes | Auto Scheduled | Create the IAM user account for Migrate for Compute Engine with the necessary roles and privileges | 1 hr | 2021 June 07 8:00 AM | 2021 June 07 9:00 AM |  | 4
83 | Yes | Auto Scheduled | Create and configure the migration manager and migration manager passwords | 1 hr | 2021 June 08 8:00 AM | 2021 June 08 9:00 AM |  | 4
84 | Yes | Auto Scheduled | Allow https for the Migrate for Compute Engine Manager instance | 1 hr | 2021 June 08 8:00 AM | 2021 June 08 9:00 AM |  | 4
85 | Yes | Auto Scheduled | Configure logging from Migrate for Compute Engine Manager | 1 hr | 2021 June 08 8:00 AM | 2021 June 08 9:00 AM |  | 4
86 | Yes | Auto Scheduled | Configure AWS as a Migrate for Compute Engine source | 1 hr | 2021 June 08 8:00 AM | 2021 June 08 9:00 AM |  | 4
87 | Yes | Auto Scheduled | Configure GCP Compute Engine API quotas to allow the needed size persistent disk | 1 hr | 2021 June 08 8:00 AM | 2021 June 08 9:00 AM |  | 4
88 | Yes | Auto Scheduled | Set up Cloud Extensions | 1 hr | 2021 June 08 8:00 AM | 2021 June 08 9:00 AM |  | 4
89 | Yes | Manually Scheduled | Copy over nginx, application servers, workers, cron schedule broker, and redis page cache | 8 hrs? | 2021 June 09 8:00 AM | 2021 June 09 5:00 PM |  | 3
90 | Yes | Auto Scheduled | Create a runbook | 1 hr | 2021 June 09 8:00 AM | 2021 June 09 9:00 AM |  | 4
91 | Yes | Auto Scheduled | Edit the runbook to only include the server clones | 1 hr | 2021 June 09 8:00 AM | 2021 June 09 9:00 AM |  | 4 | exclude the MongoDB instance...
92 | Yes | Auto Scheduled | Load the runbook into a new wave | 1 hr | 2021 June 09 8:00 AM | 2021 June 09 9:00 AM |  | 4
93 | Yes | Auto Scheduled | Validate the wave | 1 hr | 2021 June 09 8:00 AM | 2021 June 09 9:00 AM |  | 4
94 | Yes | Auto Scheduled | Create and start a Full migration job for the wave | 1 hr | 2021 June 09 8:00 AM | 2021 June 09 9:00 AM | 70 | 4
95 | Yes | Auto Scheduled | Create and run the Detach job for the wave | 1 hr | 2021 June 09 8:00 AM | 2021 June 09 9:00 AM |  | 4
96 | Yes | Auto Scheduled | Connect to the Redis instance from the Compute Engine VMs using redis-cli | 1 hr | 2021 June 09 9:00 AM | 2021 June 09 10:00 AM | 94 | 3
97 | Yes | Auto Scheduled | Configure internal http load balancing from proxy server to application servers | 1 hr | 2021 June 09 8:00 AM | 2021 June 09 9:00 AM |  | 3
98 | Yes | Manually Scheduled | Configure pub/sub queue | 8 hrs? | 2021 June 10 8:00 AM | 2021 June 10 5:00 PM |  | 3
99 | Yes | Auto Scheduled | Create a new topic in cloud pub/sub | 0.5 hrs | 2021 June 10 8:00 AM | 2021 June 10 8:30 AM |  | 4
100 | Yes | Auto Scheduled | Create a new subscription for each subscriber (cron based worker) | 1 hr | 2021 June 10 8:00 AM | 2021 June 10 9:00 AM | 94 | 4
101 | Yes | Auto Scheduled | Create a pub/sub service account and assign pub/sub publisher and subscriber roles | 0.5 hrs | 2021 June 10 8:00 AM | 2021 June 10 8:30 AM |  | 4
102 | Yes | Auto Scheduled | Install the Cloud SDK | 1 hr | 2021 June 10 8:00 AM | 2021 June 10 9:00 AM | 94 | 4
103 | Yes | Auto Scheduled | Get Python and set up a virtual environment | 1 hr | 2021 June 10 8:00 AM | 2021 June 10 9:00 AM | 94 | 4
104 | Yes | Auto Scheduled | Create a Python virtual environment and activate it in terminals for the application server and every subscriber | 1 hr | 2021 June 10 8:00 AM | 2021 June 10 9:00 AM | 94 | 4
105 | Yes | Auto Scheduled | Install the Pub/Sub Python client library using pip on each terminal | 1 hr | 2021 June 10 8:00 AM | 2021 June 10 9:00 AM | 94 | 4
106 | Yes | Auto Scheduled | Start the subscriber applications | 0.25 hrs | 2021 June 10 8:00 AM | 2021 June 10 8:15 AM | 94 | 4
107 | Yes | Auto Scheduled | Start the Publisher application | 0.25 hrs | 2021 June 10 8:00 AM | 2021 June 10 8:15 AM | 94 | 4
108 | Yes | Auto Scheduled | Develop system performance monitoring, issue logging and reporting | 4 hrs | 2021 June 11 8:00 AM | 2021 June 11 12:00 PM |  | 3
109 | Yes | Manually Scheduled | Unit Testing | 24 hrs | 2021 June 14 8:00 AM | 2021 June 16 5:00 PM |  | 2
110 | Yes | Auto Scheduled | Review application functions | 1 hr | 2021 June 14 8:00 AM | 2021 June 14 9:00 AM |  | 3
111 | Yes | Auto Scheduled | Develop unit tests for applications | 2 hrs | 2021 June 14 8:00 AM | 2021 June 14 10:00 AM | 94 | 3
112 | Yes | Auto Scheduled | develop unit tests for cron based workers | 2 hrs | 2021 June 14 8:00 AM | 2021 June 14 10:00 AM | 94 | 3
113 | Yes | Auto Scheduled | develop unit tests for cron schedule broker | 2 hrs | 2021 June 14 8:00 AM | 2021 June 14 10:00 AM | 94 | 3
114 | Yes | Auto Scheduled | Run the full suite of unit tests for all applications | 2 hrs | 2021 June 15 8:00 AM | 2021 June 15 10:00 AM | 111,112,113 | 3
115 | Yes | Auto Scheduled | Identify anomalies to product specifications | 1 hr | 2021 June 15 10:00 AM | 2021 June 15 11:00 AM | 114 | 3
116 | Yes | Auto Scheduled | Modify implementation | 4 hrs | 2021 June 16 8:00 AM | 2021 June 16 12:00 PM | 115 | 3
117 | Yes | Auto Scheduled | Re-test modified implementation | 2 hrs | 2021 June 16 1:00 PM | 2021 June 16 3:00 PM | 116 | 3
118 | Yes | Auto Scheduled | Unit testing complete | 0 days | 2021 June 16 3:00 PM | 2021 June 16 3:00 PM | 117 | 3
119 | Yes | Manually Scheduled | Integration Testing | 16 hrs | 2021 June 17 8:00 AM | 2021 June 18 5:00 PM |  | 2
120 | Yes | Auto Scheduled | Develop integration tests for application server integrations | 2 hrs | 2021 June 17 8:00 AM | 2021 June 17 10:00 AM | 94 | 3
121 | Yes | Auto Scheduled | Develop integration tests for cron based worker integrations | 2 hrs | 2021 June 17 8:00 AM | 2021 June 17 10:00 AM | 94 | 3
122 | Yes | Auto Scheduled | Run the full suite of integration tests to test component integration | 2 hrs | 2021 June 17 10:00 AM | 2021 June 17 12:00 PM | 120,121 | 3
123 | Yes | Auto Scheduled | Identify anomalies to specifications | 1 hr | 2021 June 17 1:00 PM | 2021 June 17 2:00 PM | 122 | 3
124 | Yes | Auto Scheduled | Modify configurations | 4 hrs | 2021 June 18 8:00 AM | 2021 June 18 12:00 PM | 123 | 3
125 | Yes | Auto Scheduled | Re-test modified implementation | 2 hrs | 2021 June 18 1:00 PM | 2021 June 18 3:00 PM | 124 | 3
126 | Yes | Auto Scheduled | Integration testing complete | 0 days | 2021 June 18 3:00 PM | 2021 June 18 3:00 PM | 125 | 3
127 | Yes | Auto Scheduled | Obtain approvals to proceed | 2 hrs | 2021 June 18 3:00 PM | 2021 June 18 5:00 PM | 118,126 | 2
128 | Yes | Auto Scheduled | Development complete | 0 days | 2021 June 18 5:00 PM | 2021 June 18 5:00 PM | 127 | 2
129 | Yes | Manually Scheduled | Staging | 232 hrs? | 2021 June 21 8:00 AM | 2021 July 29 5:00 PM | 127 | 1
130 | Yes | Manually Scheduled | Provision staging environment | 146 hrs? | 2021 June 21 8:00 AM | 2021 July 15 10:00 AM |  | 2
131 | Yes | Auto Scheduled | Create a bucket in your Google Cloud project | 1 hr | 2021 June 21 8:00 AM | 2021 June 21 9:00 AM |  | 3
132 | Yes | Auto Scheduled | import dev resources to staging environment | 2 hrs | 2021 June 21 8:00 AM | 2021 June 21 10:00 AM |  | 3
133 | Yes | Auto Scheduled | import dev resources into terraform | 2 hrs | 2021 June 21 8:00 AM | 2021 June 21 10:00 AM | 128 | 4
134 | Yes | Auto Scheduled | create cloud deployment manager for deploying resources to the staging environment | 1 hr | 2021 June 21 8:00 AM | 2021 June 21 9:00 AM |  | 4
135 | Yes | Auto Scheduled | deploy resources to the staging environment | 1 hr | 2021 June 21 9:00 AM | 2021 June 21 10:00 AM | 134 | 4
136 | Yes | Manually Scheduled | Configure MongoDB Atlas in GCP | 8 hrs? | 2021 June 22 8:00 AM | 2021 June 22 5:00 PM |  | 3
137 | Yes | Auto Scheduled | mongodump from AWS | 2 hrs | 2021 June 22 8:00 AM | 2021 June 22 10:00 AM |  | 4
138 | Yes | Auto Scheduled | copy the binary to the GCP bucket | 1 hr | 2021 June 22 8:00 AM | 2021 June 22 9:00 AM |  | 4
139 | Yes | Auto Scheduled | copy the binary to the MongoDB | 1 hr | 2021 June 22 8:00 AM | 2021 June 22 9:00 AM |  | 4
140 | Yes | Auto Scheduled | mongorestore in GCP | 2 hrs | 2021 June 22 8:00 AM | 2021 June 22 10:00 AM |  | 4
141 | Yes | Auto Scheduled | register MongoDB service | 1 hr | 2021 June 22 8:00 AM | 2021 June 22 9:00 AM |  | 4
142 | Yes | Manually Scheduled | Configure the Postgres Cloud SQL database | 8 hrs? | 2021 June 23 8:00 AM | 2021 June 23 5:00 PM |  | 3
143 | Yes | Auto Scheduled | Set up PostgreSQL in Google Cloud | 0.5 hrs | 2021 June 23 8:00 AM | 2021 June 23 8:30 AM |  | 4
144 | Yes | Auto Scheduled | Take a full backup from the running master server using pg_dump | 2 hrs | 2021 June 23 8:00 AM | 2021 June 23 10:00 AM |  | 4
145 | Yes | Auto Scheduled | Transfer the backup to the GCP bucket | 1 hr | 2021 June 23 8:00 AM | 2021 June 23 9:00 AM |  | 4
146 | Yes | Auto Scheduled | Transfer the backup file to the Google Cloud Postgres master | 1 hr | 2021 June 23 8:00 AM | 2021 June 23 9:00 AM |  | 4
147 | Yes | Auto Scheduled | pg_restore the backup file into the Google Cloud master | 2 hrs | 2021 June 23 8:00 AM | 2021 June 23 10:00 AM |  | 4
148 | Yes | Auto Scheduled | Register the PostgreSQL service | 0.5 hrs | 2021 June 23 8:00 AM | 2021 June 23 8:30 AM |  | 4
149 | Yes | Manually Scheduled | Copy a snapshot of the Elasticsearch cluster | 8 hrs? | 2021 June 24 8:00 AM | 2021 June 24 5:00 PM |  | 3
150 | Yes | Auto Scheduled | Purchase Elasticsearch managed service in GCP | 0.25 hrs | 2021 June 24 8:00 AM | 2021 June 24 8:15 AM |  | 4
151 | Yes | Auto Scheduled | From the Elasticsearch Service Console, create a new deployment | 1 hr | 2021 June 24 8:00 AM | 2021 June 24 9:00 AM |  | 4
152 | Yes | Auto Scheduled | Allow TCP traffic on port 9243 | 0.5 hrs | 2021 June 24 8:00 AM | 2021 June 24 8:30 AM |  | 4
153 | Yes | Auto Scheduled | register GCP cloud storage bucket as a snapshot repository | 0.5 hrs | 2021 June 24 8:00 AM | 2021 June 24 8:30 AM |  | 4
154 | Yes | Auto Scheduled | Verify the repository | 0.5 hrs | 2021 June 24 8:00 AM | 2021 June 24 8:30 AM |  | 4
155 | Yes | Auto Scheduled | Create a snapshot from AWS | 2 hrs | 2021 June 24 8:00 AM | 2021 June 24 10:00 AM |  | 4
156 | Yes | Auto Scheduled | Restore the snapshot in the GCP cluster | 2 hrs | 2021 June 24 8:00 AM | 2021 June 24 10:00 AM |  | 4
157 | Yes | Manually Scheduled | Transfer the S3 bucket | 8 hrs? | 2021 June 25 8:00 AM | 2021 June 25 5:00 PM |  | 3
158 | Yes | Auto Scheduled | Create an AWS IAM transfer user | 0.25 hrs | 2021 June 25 8:00 AM | 2021 June 25 8:15 AM |  | 4
159 | Yes | Auto Scheduled | Give the AWS IAM user the ability to perform the necessary transfer actions | 1 hr | 2021 June 25 8:00 AM | 2021 June 25 9:00 AM |  | 4
160 | Yes | Auto Scheduled | Create at least one access/secret key pair for the transfer job | 1 hr | 2021 June 25 8:00 AM | 2021 June 25 9:00 AM |  | 4
161 | Yes | Auto Scheduled | Restore any objects that are archived to Amazon Glacier | 0.5 hrs | 2021 June 25 8:00 AM | 2021 June 25 8:30 AM |  | 4
162 | Yes | Auto Scheduled | Create GCP Cloud storage bucket | 0.5 hrs | 2021 June 25 8:00 AM | 2021 June 25 8:30 AM |  | 4
163 | Yes | Auto Scheduled | Make your Cloud Storage bucket public | 0.5 hrs | 2021 June 25 8:00 AM | 2021 June 25 8:30 AM |  | 4
164 | Yes | Auto Scheduled | Reserve an external IP address | 0.5 hrs | 2021 June 25 8:00 AM | 2021 June 25 8:30 AM |  | 4
165 | Yes | Auto Scheduled | Create the external HTTP(S) load balancer | 1 hr | 2021 June 25 8:00 AM | 2021 June 25 9:00 AM |  | 4
166 | Yes | Auto Scheduled | Set up the transfer job on the transfer page to run | 2 hrs | 2021 June 25 8:00 AM | 2021 June 25 10:00 AM |  | 4
167 | Yes | Auto Scheduled | Send https://assets.postmedia.com traffic to your backend bucket | 0.5 hrs | 2021 June 25 8:00 AM | 2021 June 25 8:30 AM |  | 4
168 | Yes | Manually Scheduled | Integration Testing | 24 hrs | 2021 June 28 8:00 AM | 2021 June 30 5:00 PM |  | 3
169 | Yes | Auto Scheduled | Develop integration tests for MongoDB | 2 hrs | 2021 June 28 8:00 AM | 2021 June 28 10:00 AM | 141 | 4
170 | Yes | Auto Scheduled | Develop Integration tests for PostgreSQL | 2 hrs | 2021 June 28 8:00 AM | 2021 June 28 10:00 AM | 148 | 4
171 | Yes | Auto Scheduled | Develop integration tests for Elasticsearch cluster | 2 hrs | 2021 June 28 8:00 AM | 2021 June 28 10:00 AM | 156 | 4
172 | Yes | Auto Scheduled | Test resolving cloud storage files | 2 hrs | 2021 June 28 8:00 AM | 2021 June 28 10:00 AM | 166 | 4
173 | Yes | Auto Scheduled | Run the full suite of integration tests to test component integration | 3 hrs | 2021 June 29 8:00 AM | 2021 June 29 11:00 AM | 169,170,171 | 4
174 | Yes | Auto Scheduled | Identify anomalies to specifications | 1 hr | 2021 June 29 11:00 AM | 2021 June 29 12:00 PM | 173 | 4
175 | Yes | Auto Scheduled | Modify configurations | 4 hrs | 2021 June 29 1:00 PM | 2021 June 29 5:00 PM | 174 | 4
176 | Yes | Auto Scheduled | Re-test modified implementation | 2 hrs | 2021 June 30 8:00 AM | 2021 June 30 10:00 AM | 175 | 4
177 | Yes | Auto Scheduled | Integration testing complete | 0 hrs | 2021 June 30 10:00 AM | 2021 June 30 10:00 AM | 176 | 4
178 | Yes | Manually Scheduled | End-to-end testing | 16 hrs | 2021 July 01 8:00 AM | 2021 July 02 5:00 PM |  | 3
179 | Yes | Auto Scheduled | Develop end-to-end tests and test plans based on architecture specifications | 2 hrs | 2021 July 01 8:00 AM | 2021 July 01 10:00 AM | 141,148,156,166 | 4
180 | Yes | Auto Scheduled | Run end-to-end scenarios | 2 hrs | 2021 July 01 10:00 AM | 2021 July 01 12:00 PM | 179 | 4
181 | Yes | Auto Scheduled | Identify anomalies to specification | 1 hr | 2021 July 01 1:00 PM | 2021 July 01 2:00 PM | 180 | 4
182 | Yes | Auto Scheduled | Modify configurations | 4 hrs | 2021 July 01 2:00 PM | 2021 July 02 9:00 AM | 181 | 4
183 | Yes | Auto Scheduled | Re-test modified implementation | 2 hrs | 2021 July 02 9:00 AM | 2021 July 02 11:00 AM | 182 | 4
184 | Yes | Auto Scheduled | End-to-end testing complete | 0 hrs | 2021 July 02 11:00 AM | 2021 July 02 11:00 AM | 183 | 4
185 | Yes | Manually Scheduled | Pilot | 48 hrs | 2021 July 05 8:00 AM | 2021 July 12 5:00 PM | 176,184 | 2
186 | Yes | Auto Scheduled | Identify test group | 4 hrs | 2021 July 01 8:00 AM | 2021 July 01 12:00 PM |  | 3
187 | Yes | Auto Scheduled | Configure environment to allow user interaction for testing | 2 hrs | 2021 July 05 8:00 AM | 2021 July 05 10:00 AM |  | 3
188 | Yes | Auto Scheduled | Start running staging environment | 1 hr | 2021 July 05 8:00 AM | 2021 July 05 9:00 AM |  | 3
189 | Yes | Auto Scheduled | Perform pilot and test all identified scenarios | 5 hrs | 2021 July 05 8:00 AM | 2021 July 05 2:00 PM |  | 3
190 | Yes | Auto Scheduled | Obtain user feedback | 2 hrs | 2021 July 05 8:00 AM | 2021 July 05 10:00 AM |  | 3
191 | Yes | Auto Scheduled | Evaluate performance and functionality | 2 hrs | 2021 July 06 8:00 AM | 2021 July 06 10:00 AM |  | 3
192 | Yes | Auto Scheduled | Make necessary changes to the code base based on evaluation | 16 hrs | 2021 July 06 8:00 AM | 2021 July 07 5:00 PM |  | 3
193 | Yes | Auto Scheduled | Pilot complete | 0 hrs | 2021 July 07 8:00 AM | 2021 July 07 8:00 AM |  | 3
194 | Yes | Auto Scheduled | Obtain approvals to proceed | 2 hrs | 2021 July 08 8:00 AM | 2021 July 08 10:00 AM |  | 2
195 | Yes | Auto Scheduled | Staging complete | 0 hrs | 2021 July 08 10:00 AM | 2021 July 08 10:00 AM | 194 | 2
196 | Yes | Manually Scheduled | Production | 148 hrs? | 2021 July 09 8:00 AM | 2021 August 04 12:00 PM |  | 1
197 | Yes | Manually Scheduled | Documentation and Training | 24 hrs | 2021 July 09 8:00 AM | 2021 July 13 5:00 PM |  | 2
198 | Yes | Auto Scheduled | Determine post go live resource needs | 2 hrs | 2021 July 09 8:00 AM | 2021 July 09 10:00 AM |  | 3
199 | Yes | Auto Scheduled | Prepare production runbook | 2 hrs | 2021 July 09 8:00 AM | 2021 July 09 10:00 AM |  | 3
200 | Yes | Auto Scheduled | Review production runbook | 1 hr | 2021 July 09 8:00 AM | 2021 July 09 9:00 AM |  | 3
201 | Yes | Auto Scheduled | Incorporate troubleshooting documentation feedback | 1 hr | 2021 July 09 8:00 AM | 2021 July 09 9:00 AM |  | 3
202 | Yes | Auto Scheduled | Review deployment methodology | 1 hr | 2021 July 09 8:00 AM | 2021 July 09 9:00 AM |  | 3
203 | Yes | Auto Scheduled | Review rollout plan | 1 hr | 2021 July 12 8:00 AM | 2021 July 12 9:00 AM |  | 3
204 | Yes | Auto Scheduled | Review rollback strategy | 1 hr | 2021 July 12 8:00 AM | 2021 July 12 9:00 AM |  | 3
205 | Yes | Auto Scheduled | Define rollout strategy | 1 hr | 2021 July 12 8:00 AM | 2021 July 12 9:00 AM |  | 3
206 | Yes | Auto Scheduled | Confirm changeover window | 1 hr | 2021 July 12 8:00 AM | 2021 July 12 9:00 AM |  | 3
207 | Yes | Auto Scheduled | Secure deployment resources | 1 hr | 2021 July 12 8:00 AM | 2021 July 12 9:00 AM |  | 3
208 | Yes | Auto Scheduled | Train maintenance team members | 6 hrs | 2021 July 13 8:00 AM | 2021 July 13 3:00 PM |  | 3
209 | Yes | Auto Scheduled | Documentation complete | 0 hrs | 2021 July 13 8:00 AM | 2021 July 13 8:00 AM |  | 3
210 | Yes | Auto Scheduled | Confirm go/no go decision | 1 hr | 2021 July 13 8:00 AM | 2021 July 13 9:00 AM |  | 2
211 | Yes | Manually Scheduled | Provision production environment | 32 hrs? | 2021 July 14 8:00 AM | 2021 July 19 5:00 PM |  | 2
212 | Yes | Auto Scheduled | import staging resources into terraform | 1 hr | 2021 July 14 8:00 AM | 2021 July 14 9:00 AM | 194 | 3
213 | Yes | Auto Scheduled | create cloud deployment manager for deploying resources to the production environment | 0.5 hrs | 2021 July 14 9:00 AM | 2021 July 14 9:30 AM | 212 | 3
214 | Yes | Auto Scheduled | deploy resources to the production environment | 0.5 hrs | 2021 July 14 9:30 AM | 2021 July 14 10:00 AM | 213 | 3
215 | Yes | Manually Scheduled | Migrate Postgres to GCP cloud SQL | 8 hrs? | 2021 July 15 8:00 AM | 2021 July 15 5:00 PM |  | 3
216 | Yes | Auto Scheduled | Allow data replication through VPN | 1 hr | 2021 July 15 8:00 AM | 2021 July 15 9:00 AM |  | 4
217 | Yes | Auto Scheduled | Set up Postgres SQL replication with AWS as the MASTER and GCP as the SLAVE | 1 hr | 2021 July 15 8:00 AM | 2021 July 15 9:00 AM |  | 4
218 | Yes | Auto Scheduled | When data replication is completed, promote GCP to the MASTER | 1 hr | 2021 July 15 8:00 AM | 2021 July 15 9:00 AM |  | 4
219 | Yes | Manually Scheduled | Migrate GCP MongoDB Atlas | 8 hrs | 2021 July 16 8:00 AM | 2021 July 16 5:00 PM |  | 3
220 | Yes | Auto Scheduled | Launch the same number of source instances as AWS MongoDB replica set | 0.5 hrs | 2021 July 16 8:00 AM | 2021 July 16 8:30 AM |  | 4
221 | Yes | Auto Scheduled | Update bindIp of new launch instances to use private Ip of instance and restart new mongo instances | 0.25 hrs | 2021 July 16 8:00 AM | 2021 July 16 8:15 AM |  | 4
222 | Yes | Auto Scheduled | Login to the primary instance and add all GCP instances as a replica wait until stateStr becomes SECONDARY state for all GCP instances | 1 hr | 2021 July 16 8:00 AM | 2021 July 16 9:00 AM |  | 4
223 | Yes | Auto Scheduled | Update route53 host to point to GCP | 0.25 hrs | 2021 July 16 8:00 AM | 2021 July 16 8:15 AM |  | 4
224 | Yes | Auto Scheduled | redeploy all mongodb clients to refresh DNS entries in case of any caching | 0.5 hrs | 2021 July 16 8:00 AM | 2021 July 16 8:30 AM |  | 4
225 | Yes | Auto Scheduled | set GCP replicas priority higher than AWS and give voting rights to GCP replicas | 0.5 hrs | 2021 July 16 8:00 AM | 2021 July 16 8:30 AM |  | 4
226 | Yes | Auto Scheduled | Remove the AWS replicas from the set | 0.25 hrs | 2021 July 16 8:00 AM | 2021 July 16 8:15 AM |  | 4
227 | Yes | Auto Scheduled | Initiate leader election and step down the old AWS primary | 0.25 hrs | 2021 July 16 8:00 AM | 2021 July 16 8:15 AM |  | 4
228 | Yes | Auto Scheduled | Remove the final AWS instance from the set | 0.25 hrs | 2021 July 16 8:00 AM | 2021 July 16 8:15 AM |  | 4
229 | Yes | Manually Scheduled | reindex ElasticSearch cluster | 8 hrs | 2021 July 19 8:00 AM | 2021 July 19 5:00 PM |  | 3
230 | Yes | Auto Scheduled | Add the reindex.remote.whitelist user setting to the AWS Elasticsearch cluster | 1 hr | 2021 July 19 8:00 AM | 2021 July 19 9:00 AM |  | 4
231 | Yes | Auto Scheduled | Allow TCP traffic on port 9243 | 1 hr | 2021 July 19 8:00 AM | 2021 July 19 9:00 AM |  | 4
232 | Yes | Auto Scheduled | From the API Console create the destination index on Elasticsearch Service | 1 hr | 2021 July 19 8:00 AM | 2021 July 19 9:00 AM |  | 4
233 | Yes | Auto Scheduled | Copy the index from the remote cluster | 1 hr | 2021 July 19 8:00 AM | 2021 July 19 9:00 AM |  | 4
234 | Yes | Auto Scheduled | When the reindex job completes, set the refresh_interval and number_of_replicas to the desired values | 1 hr | 2021 July 19 8:00 AM | 2021 July 19 9:00 AM |  | 4
235 | Yes | Auto Scheduled | Once reindexing is complete and the status of the new index is green, you can delete the old index | 1 hr | 2021 July 19 8:00 AM | 2021 July 19 9:00 AM |  | 4
236 | Yes | Auto Scheduled | Run test suites in production for sanity check | 2 hrs | 2021 July 19 9:00 AM | 2021 July 19 11:00 AM | 218,228,235 | 2
237 | Yes | Manually Scheduled | Deployment | 8 hrs | 2021 July 20 8:00 AM | 2021 July 20 5:00 PM | 236 | 2
238 | Yes | Auto Scheduled | Set up 50/50 weighted DNS in Route 53 for both platforms | 1 hr | 2021 July 20 8:00 AM | 2021 July 20 9:00 AM |  | 3
239 | Yes | Auto Scheduled | Create a GCP managed zone | 1 hr | 2021 July 20 8:00 AM | 2021 July 20 9:00 AM |  | 3
240 | Yes | Auto Scheduled | Export your DNS configuration from AWS | 1 hr | 2021 July 20 8:00 AM | 2021 July 20 9:00 AM |  | 3
241 | Yes | Auto Scheduled | Import the record set in GCP | 1 hr | 2021 July 20 8:00 AM | 2021 July 20 9:00 AM |  | 3
242 | Yes | Auto Scheduled | Verify DNS propagation | 1 hr | 2021 July 20 8:00 AM | 2021 July 20 9:00 AM |  | 3
243 | Yes | Auto Scheduled | Update your registrar's name server records | 1 hr | 2021 July 20 8:00 AM | 2021 July 20 9:00 AM |  | 3
244 | Yes | Auto Scheduled | Complete post go-live validation | 4 hrs | 2021 July 21 8:00 AM | 2021 July 21 12:00 PM |  | 2
245 | Yes | Auto Scheduled | Remove managed zones in AWS | 5 hrs | 2021 July 21 1:00 PM | 2021 July 22 9:00 AM | 244 | 2
246 | Yes | Auto Scheduled | Production complete | 0 hrs | 2021 July 21 8:00 AM | 2021 July 21 8:00 AM |  | 2
247 | Yes | Manually Scheduled | Post Implementation Review | 16 hrs | 2021 July 22 8:00 AM | 2021 July 23 5:00 PM |  | 1
248 | Yes | Auto Scheduled | Get acceptance of deliverables | 1 hr | 2021 July 22 8:00 AM | 2021 July 22 9:00 AM |  | 2
249 | Yes | Auto Scheduled | Evaluate stakeholder satisfaction | 1 hr | 2021 July 22 8:00 AM | 2021 July 22 9:00 AM |  | 2
250 | Yes | Auto Scheduled | Review project goals, timeline, budget, success metrics, and major events | 1 hr | 2021 July 23 8:00 AM | 2021 July 23 9:00 AM |  | 2
251 | Yes | Auto Scheduled | Discuss what worked and what can be improved for future projects | 2 hrs | 2021 July 23 8:00 AM | 2021 July 23 10:00 AM |  | 2
252 | Yes | Auto Scheduled | Document lessons learned and create action plan to address feedback | 2 hrs | 2021 July 23 8:00 AM | 2021 July 23 10:00 AM |  | 2
253 | Yes | Auto Scheduled | Distribute to team members | 2 hrs | 2021 July 23 8:00 AM | 2021 July 23 10:00 AM |  | 2
254 | Yes | Auto Scheduled | Post implementation review complete | 0 days | 2021 July 23 8:00 AM | 2021 July 23 8:00 AM |  | 2
255 | Yes | Manually Scheduled | Handover to business and maintenance team | 16 hrs | 2021 July 26 8:00 AM | 2021 July 27 5:00 PM |  | 1
256 | Yes | Auto Scheduled | Reassign resources | 2 hrs | 2021 July 26 8:00 AM | 2021 July 26 10:00 AM |  | 2
257 | Yes | Auto Scheduled | Identify key roles and responsibilities for maintenance | 2 hrs | 2021 July 26 8:00 AM | 2021 July 26 10:00 AM |  | 2
258 | Yes | Auto Scheduled | Provide supporting documentation | 2 hrs | 2021 July 26 8:00 AM | 2021 July 26 10:00 AM |  | 2
259 | Yes | Auto Scheduled | Walk the team through the day to day of the maintenance | 4 hrs | 2021 July 27 8:00 AM | 2021 July 27 12:00 PM |  | 2
260 | Yes | Auto Scheduled | Kickoff maintenance teamwork | 2 hrs | 2021 July 27 8:00 AM | 2021 July 27 10:00 AM |  | 2
261 | Yes | Auto Scheduled | Reconfigure weighted DNS to GCP only | 2 hrs | 2021 July 27 8:00 AM | 2021 July 27 10:00 AM | 248 | 2
262 | Yes | Auto Scheduled | Decommission AWS resources | 2 hrs | 2021 July 27 8:00 AM | 2021 July 27 10:00 AM | 248 | 2
263 | Yes | Auto Scheduled | Project end | 0 days | 2021 July 27 8:00 AM | 2021 July 27 8:00 AM |  | 1

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
0 |  |  | Work |  |  |  |  | 100% | $0.00/h | 0
1 | Project Sponsor | P | Work |  |  |  |  | 100% | $0.00/h | 0
2 | Enterprise Architect | E | Work |  |  |  |  | 100% | $0.00/h | 0
3 | Developer | D | Work |  |  |  |  | 100% | $0.00/h | 0
4 | Testers | T | Work |  |  |  |  | 100% | $0.00/h | 0
5 | Technical Staff | T | Work |  |  |  |  | 100% | $0.00/h | 0
6 | Functional Manager | F | Work |  |  |  |  | 100% | $0.00/h | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Conduct needs analysis | Enterprise Architect | 0 | 4h | 100%
Identify stakeholder needs, influence on project | Enterprise Architect | 0 | 4h | 100%
Determine project scope | Enterprise Architect | 0 | 2h | 100%
Develop a proposal | Enterprise Architect | 0 | 4h | 100%
Define preliminary resources | Enterprise Architect | 0 | 2h | 100%
Secure project sponsorship | Enterprise Architect | 0 | 1h | 100%
Secure project sponsorship | Project Sponsor | 0 | 1h | 100%
Secure core resources | Enterprise Architect | 0 | 4h | 100%
Secure core resources | Functional Manager | 0 | 4h | 100%
Secure core resources | Project Sponsor | 0 | 4h | 100%
Identify security and compliance requirements | Enterprise Architect | 0 | 2h | 100%
Identify security and compliance requirements | Project Sponsor | 0 | 2h | 100%
Create governance workbook | Enterprise Architect | 0 | 3h | 100%
Create governance workbook | Project Sponsor | 0 | 3h | 100%
Identify all the application environments | Enterprise Architect | 0 | 2h | 100%
Perform application walkthroughs | Enterprise Architect | 0 | 1h | 100%
Perform application walkthroughs | Technical Staff | 0 | 1h | 100%
Establish pre-migration performance baseline in AWS CloudWatch dashboard | Enterprise Architect | 0 | 4h | 100%
Determine options for google cloud services | Enterprise Architect | 0 | 5h | 100%
Identify application integration requirements | Enterprise Architect | 0 | 3h | 100%
Perform deployment assessment | Enterprise Architect | 0 | 3h | 100%
Identify data that does not require migration - purge/archive based on retention policies | Enterprise Architect | 0 | 3h | 100%
Identify data that requires cleanup for integrity | Enterprise Architect | 0 | 2h | 100%
Define migration phases | Enterprise Architect | 0 | 3h | 100%
Define data migration approach | Enterprise Architect | 0 | 3h | 100%
Identify production cutover window | Enterprise Architect | 0 | 1h | 100%
Perform cost benefit analysis | Enterprise Architect | 0 | 4h | 100%
Recommend an option and obtain approvals | Enterprise Architect | 0 | 0.5h | 100%
Recommend an option and obtain approvals | Project Sponsor | 0 | 0.5h | 100%
Scope all deliverables, objectives, quality, cost | Enterprise Architect | 0 | 4h | 100%
Establish organization structure | Enterprise Architect | 0 | 1h | 100%
Establish organization structure | Functional Manager | 0 | 1h | 100%
Define progress reporting - status reports, burndown, interdependency, schedule/plan | Enterprise Architect | 0 | 2h | 100%
Develop a project charter | Enterprise Architect | 0 | 3h | 100%
Review architecture specifications/budget with team | Enterprise Architect | 0 | 2h | 100%
Review architecture specifications/budget with team | Developer | 0 | 2h | 100%
Incorporate feedback on architecture specifications | Enterprise Architect | 0 | 1h | 100%
Define milestones and high level tasks | Enterprise Architect | 0 | 1h | 100%
Define responsibilties for team members | Enterprise Architect | 0 | 1h | 100%
Assign resources to tasks, revise schedule depending on availability | Enterprise Architect | 0 | 3h | 100%
Develop preliminary budget | Enterprise Architect | 0 | 3h | 100%
Define test plans for unit, integration and performance testing | Enterprise Architect | 0 | 2h | 100%
Define rollout plan | Enterprise Architect | 0 | 3h | 100%
Identify risks, probability and impact | Enterprise Architect | 0 | 2h | 100%
Define rollback strategy | Enterprise Architect | 0 | 1h | 100%
Develop delivery timeline | Enterprise Architect | 0 | 1h | 100%
Prepare transition readiness plan | Enterprise Architect | 0 | 1h | 100%
Obtain approvals to proceed (concept, timeline, budget) | Project Sponsor | 0 | 0h | 100%
Obtain approvals to proceed (concept, timeline, budget) | Enterprise Architect | 0 | 0h | 100%
Set up recurring business meetings | Enterprise Architect | 0 | 1h | 100%
Secure required resources | Enterprise Architect | 0 | 1h | 100%
Hold Kick-Off | Developer | 0 | 2h | 100%
Hold Kick-Off | Enterprise Architect | 0 | 2h | 100%
Hold Kick-Off | Functional Manager | 0 | 2h | 100%
Hold Kick-Off | Project Sponsor | 0 | 2h | 100%
Acquire access to current applications, data stores, and services | Enterprise Architect | 0 | 3h | 100%
Acquire access to current applications, data stores, and services | Functional Manager | 0 | 3h | 100%
Acquire access to current applications, data stores, and services | Technical Staff | 0 | 3h | 100%
Set up a Google Cloud account, organization, and infrastructure project | Developer | 0 | 2h | 100%
Create cloud source repositories | Developer | 0 | 2h | 100%
Create a prioritized inventory of the migration components | Enterprise Architect | 0 | 1h | 100%
Identify requirements for connectivity - VPN, VPC, Peering | Enterprise Architect | 0 | 4h | 100%
Develop functional specifications | Enterprise Architect | 0 | 2h | 100%
Review functional specifications | Enterprise Architect | 0 | 1h | 100%
Review functional specifications | Developer | 0 | 1h | 100%
Incorporate feedback into functional specifications | Enterprise Architect | 0 | 1h | 100%
Establish cloud KPIs | Enterprise Architect | 0 | 2h | 100%
Obtain approval to proceed | Enterprise Architect | 0 | 2h | 100%
Review functional specifications | Developer | 0 | 2h | 100%
Review functional specifications | Enterprise Architect | 0 | 2h | 100%
Assign development staff | Enterprise Architect | 0 | 2h | 100%
Assign development staff | Functional Manager | 0 | 2h | 100%
Create images from the EC2 instances we intend to migrate | Developer | 0 | 1h | 100%
Create cloned instances from the EC2 instances we intend to migrate | Developer | 0 | 1h | 100%
Modify tags for identifying the cloned machines you want to migrate | Developer | 0 | 2h | 100%
Install the Migrate for Compute Engine Linux package to reconfigure Linux VMs for Google Cloud | Developer | 0 | 2h | 100%
Ensure that our cloned instances are not running | Developer | 0 | 2h | 100%
Set up a Google Cloud Virtual Private Cloud | Developer | 0 | 1h | 100%
Set up networks, access, and firewall rules in migration environment | Developer | 0 | 1h | 100%
Create the Migrate for Compute Engine IAM group in AWS using the Configuration for AWS CloudFormation | Developer | 0 | 1h | 100%
Create the AWS IAM user account for Migrate for Compute Engine with programmatic access | Developer | 0 | 1h | 100%
Download the AWS IAM user CSV with the access keys and store securely | Developer | 0 | 1h | 100%
Create Google Cloud roles and service accounts via Cloud Shell | Developer | 0 | 2h | 100%
Create the IAM user account for Migrate for Compute Engine with the necessary roles and privileges | Developer | 0 | 1h | 100%
Create and configure the migration manager and migration manager passwords | Developer | 0 | 1h | 100%
Allow https for the Migrate for Compute Engine Manager instance | Developer | 0 | 1h | 100%
Configure logging from Migrate for Compute Engine Manager | Developer | 0 | 1h | 100%
Configure AWS as a Migrate for Compute Engine source | Developer | 0 | 1h | 100%
Configure GCP Compute Engine API quotas to allow the needed size persistent disk | Developer | 0 | 1h | 100%
Set up Cloud Extensions | Developer | 0 | 1h | 100%
Create a runbook | Developer | 0 | 1h | 100%
Edit the runbook to only include the server clones | Developer | 0 | 1h | 100%
Load the runbook into a new wave | Developer | 0 | 1h | 100%
Validate the wave | Developer | 0 | 1h | 100%
Create and start a Full migration job for the wave | Developer | 0 | 1h | 100%
Create and run the Detach job for the wave | Developer | 0 | 1h | 100%
Connect to the Redis instance from the Compute Engine VMs using redis-cli | Developer | 0 | 1h | 100%
Configure internal http load balancing from proxy server to application servers | Developer | 0 | 1h | 100%
Create a new topic in cloud pub/sub | Developer | 0 | 0.5h | 100%
Create a new subscription for each subscriber (cron based worker) | Developer | 0 | 1h | 100%
Create a pub/sub service account and assign pub/sub publisher and subscriber roles | Developer | 0 | 0.5h | 100%
Install the Cloud SDK | Developer | 0 | 1h | 100%
Get Python and set up a virtual environment | Developer | 0 | 1h | 100%
Create a Python virtual environment and activate it in terminals for the application server and every subscriber | Developer | 0 | 1h | 100%
Install the Pub/Sub Python client library using pip on each terminal | Developer | 0 | 1h | 100%
Start the subscriber applications | Developer | 0 | 0.25h | 100%
Start the Publisher application | Developer | 0 | 0.25h | 100%
Develop system performance monitoring, issue logging and reporting | Enterprise Architect | 0 | 4h | 100%
Review application functions | Developer | 0 | 1h | 100%
Review application functions | Enterprise Architect | 0 | 1h | 100%
Develop unit tests for applications | Developer | 0 | 2h | 100%
develop unit tests for cron based workers | Developer | 0 | 2h | 100%
develop unit tests for cron schedule broker | Developer | 0 | 2h | 100%
Run the full suite of unit tests for all applications | Developer | 0 | 2h | 100%
Identify anomalies to product specifications | Developer | 0 | 1h | 100%
Modify implementation | Developer | 0 | 4h | 100%
Re-test modified implementation | Developer | 0 | 2h | 100%
Develop integration tests for application server integrations | Developer | 0 | 2h | 100%
Develop integration tests for cron based worker integrations | Developer | 0 | 2h | 100%
Run the full suite of integration tests to test component integration | Developer | 0 | 2h | 100%
Identify anomalies to specifications | Developer | 0 | 1h | 100%
Modify configurations | Developer | 0 | 4h | 100%
Re-test modified implementation | Developer | 0 | 2h | 100%
Integration testing complete | Developer | 0 | 0h | 100%
Obtain approvals to proceed | Enterprise Architect | 0 | 2h | 100%
Obtain approvals to proceed | Project Sponsor | 0 | 2h | 100%
Create a bucket in your Google Cloud project | Developer | 0 | 1h | 100%
import dev resources into terraform | Developer | 0 | 2h | 100%
create cloud deployment manager for deploying resources to the staging environment | Developer | 0 | 1h | 100%
deploy resources to the staging environment | Developer | 0 | 1h | 100%
mongodump from AWS | Developer | 0 | 2h | 100%
copy the binary to the GCP bucket | Developer | 0 | 1h | 100%
copy the binary to the MongoDB | Developer | 0 | 1h | 100%
mongorestore in GCP | Developer | 0 | 2h | 100%
register MongoDB service | Developer | 0 | 1h | 100%
Set up PostgreSQL in Google Cloud | Developer | 0 | 0.5h | 100%
Take a full backup from the running master server using pg_dump | Developer | 0 | 2h | 100%
Transfer the backup to the GCP bucket | Developer | 0 | 1h | 100%
Transfer the backup file to the Google Cloud Postgres master | Developer | 0 | 1h | 100%
pg_restore the backup file into the Google Cloud master | Developer | 0 | 2h | 100%
Register the PostgreSQL service | Developer | 0 | 0.5h | 100%
Purchase Elasticsearch managed service in GCP | Developer | 0 | 0.25h | 100%
From the Elasticsearch Service Console, create a new deployment | Developer | 0 | 1h | 100%
Allow TCP traffic on port 9243 | Developer | 0 | 0.5h | 100%
register GCP cloud storage bucket as a snapshot repository | Developer | 0 | 0.5h | 100%
Verify the repository | Developer | 0 | 0.5h | 100%
Create a snapshot from AWS | Developer | 0 | 2h | 100%
Restore the snapshot in the GCP cluster | Developer | 0 | 2h | 100%
Create an AWS IAM transfer user | Developer | 0 | 0.25h | 100%
Give the AWS IAM user the ability to perform the necessary transfer actions | Developer | 0 | 1h | 100%
Create at least one access/secret key pair for the transfer job | Developer | 0 | 1h | 100%
Restore any objects that are archived to Amazon Glacier | Developer | 0 | 0.5h | 100%
Create GCP Cloud storage bucket | Developer | 0 | 0.5h | 100%
Make your Cloud Storage bucket public | Developer | 0 | 0.5h | 100%
Reserve an external IP address | Developer | 0 | 0.5h | 100%
Create the external HTTP(S) load balancer | Developer | 0 | 1h | 100%
Set up the transfer job on the transfer page to run | Developer | 0 | 2h | 100%
Send https://assets.postmedia.com traffic to your backend bucket | Developer | 0 | 0.5h | 100%
Develop integration tests for MongoDB | Developer | 0 | 2h | 100%
Develop Integration tests for PostgreSQL | Developer | 0 | 2h | 100%
Develop integration tests for Elasticsearch cluster | Developer | 0 | 2h | 100%
Test resolving cloud storage files | Developer | 0 | 2h | 100%
Run the full suite of integration tests to test component integration | Developer | 0 | 3h | 100%
Identify anomalies to specifications | Developer | 0 | 1h | 100%
Modify configurations | Developer | 0 | 4h | 100%
Re-test modified implementation | Developer | 0 | 2h | 100%
Develop end-to-end tests and test plans based on architecture specifications | Developer | 0 | 2h | 100%
Run end-to-end scenarios | Developer | 0 | 2h | 100%
Identify anomalies to specification | Developer | 0 | 1h | 100%
Modify configurations | Developer | 0 | 4h | 100%
Re-test modified implementation | Developer | 0 | 2h | 100%
Identify test group | Enterprise Architect | 0 | 4h | 100%
Configure environment to allow user interaction for testing | Developer | 0 | 2h | 100%
Start running staging environment | Developer | 0 | 1h | 100%
Perform pilot and test all identified scenarios | Enterprise Architect | 0 | 5h | 100%
Perform pilot and test all identified scenarios | Testers | 0 | 5h | 100%
Obtain user feedback | Enterprise Architect | 0 | 2h | 100%
Obtain user feedback | Testers | 0 | 2h | 100%
Evaluate performance and functionality | Enterprise Architect | 0 | 2h | 100%
Make necessary changes to the code base based on evaluation | Developer | 0 | 16h | 100%
Obtain approvals to proceed | Enterprise Architect | 0 | 2h | 100%
Obtain approvals to proceed | Project Sponsor | 0 | 2h | 100%
Determine post go live resource needs | Enterprise Architect | 0 | 2h | 100%
Determine post go live resource needs | Functional Manager | 0 | 2h | 100%
Prepare production runbook | Developer | 0 | 2h | 100%
Prepare production runbook | Enterprise Architect | 0 | 2h | 100%
Review production runbook | Developer | 0 | 1h | 100%
Review production runbook | Enterprise Architect | 0 | 1h | 100%
Incorporate troubleshooting documentation feedback | Enterprise Architect | 0 | 1h | 100%
Review deployment methodology | Developer | 0 | 1h | 100%
Review deployment methodology | Enterprise Architect | 0 | 1h | 100%
Review rollout plan | Developer | 0 | 1h | 100%
Review rollout plan | Enterprise Architect | 0 | 1h | 100%
Review rollback strategy | Developer | 0 | 1h | 100%
Review rollback strategy | Enterprise Architect | 0 | 1h | 100%
Define rollout strategy | Enterprise Architect | 0 | 1h | 100%
Confirm changeover window | Enterprise Architect | 0 | 1h | 100%
Confirm changeover window | Technical Staff | 0 | 1h | 100%
Secure deployment resources | Enterprise Architect | 0 | 1h | 100%
Secure deployment resources | Functional Manager | 0 | 1h | 100%
Train maintenance team members | Enterprise Architect | 0 | 6h | 100%
Train maintenance team members | Functional Manager | 0 | 6h | 100%
Train maintenance team members | Technical Staff | 0 | 6h | 100%
Confirm go/no go decision | Enterprise Architect | 0 | 1h | 100%
Confirm go/no go decision | Project Sponsor | 0 | 1h | 100%
import staging resources into terraform | Developer | 0 | 1h | 100%
create cloud deployment manager for deploying resources to the production environment | Developer | 0 | 0.5h | 100%
deploy resources to the production environment | Developer | 0 | 0.5h | 100%
Allow data replication through VPN | Developer | 0 | 1h | 100%
Set up Postgres SQL replication with AWS as the MASTER and GCP as the SLAVE | Developer | 0 | 1h | 100%
When data replication is completed, promote GCP to the MASTER | Developer | 0 | 1h | 100%
Launch the same number of source instances as AWS MongoDB replica set | Developer | 0 | 0.5h | 100%
Update bindIp of new launch instances to use private Ip of instance and restart new mongo instances | Developer | 0 | 0.25h | 100%
Login to the primary instance and add all GCP instances as a replica wait until stateStr becomes SECONDARY state for all GCP instances | Developer | 0 | 1h | 100%
Update route53 host to point to GCP | Developer | 0 | 0.25h | 100%
redeploy all mongodb clients to refresh DNS entries in case of any caching | Developer | 0 | 0.5h | 100%
set GCP replicas priority higher than AWS and give voting rights to GCP replicas | Developer | 0 | 0.5h | 100%
Remove the AWS replicas from the set | Developer | 0 | 0.25h | 100%
Initiate leader election and step down the old AWS primary | Developer | 0 | 0.25h | 100%
Remove the final AWS instance from the set | Developer | 0 | 0.25h | 100%
Add the reindex.remote.whitelist user setting to the AWS Elasticsearch cluster | Developer | 0 | 1h | 100%
Allow TCP traffic on port 9243 | Developer | 0 | 1h | 100%
From the API Console create the destination index on Elasticsearch Service | Developer | 0 | 1h | 100%
Copy the index from the remote cluster | Developer | 0 | 1h | 100%
When the reindex job completes, set the refresh_interval and number_of_replicas to the desired values | Developer | 0 | 1h | 100%
Once reindexing is complete and the status of the new index is green, you can delete the old index | Developer | 0 | 1h | 100%
Run test suites in production for sanity check | Developer | 0 | 2h | 100%
Set up 50/50 weighted DNS in Route 53 for both platforms | Developer | 0 | 1h | 100%
Create a GCP managed zone | Developer | 0 | 1h | 100%
Export your DNS configuration from AWS | Developer | 0 | 1h | 100%
Import the record set in GCP | Developer | 0 | 1h | 100%
Verify DNS propagation | Developer | 0 | 1h | 100%
Update your registrar's name server records | Developer | 0 | 1h | 100%
Complete post go-live validation | Enterprise Architect | 0 | 4h | 100%
Remove managed zones in AWS | Developer | 0 | 5h | 100%
Get acceptance of deliverables | Enterprise Architect | 0 | 1h | 100%
Get acceptance of deliverables | Project Sponsor | 0 | 1h | 100%
Evaluate stakeholder satisfaction | Enterprise Architect | 0 | 1h | 100%
Review project goals, timeline, budget, success metrics, and major events | Enterprise Architect | 0 | 1h | 100%
Review project goals, timeline, budget, success metrics, and major events | Developer | 0 | 1h | 100%
Review project goals, timeline, budget, success metrics, and major events | Functional Manager | 0 | 1h | 100%
Discuss what worked and what can be improved for future projects | Enterprise Architect | 0 | 2h | 100%
Discuss what worked and what can be improved for future projects | Developer | 0 | 2h | 100%
Discuss what worked and what can be improved for future projects | Functional Manager | 0 | 2h | 100%
Discuss what worked and what can be improved for future projects | Project Sponsor | 0 | 2h | 100%
Document lessons learned and create action plan to address feedback | Enterprise Architect | 0 | 2h | 100%
Distribute to team members | Enterprise Architect | 0 | 2h | 100%
Reassign resources | Enterprise Architect | 0 | 2h | 100%
Reassign resources | Functional Manager | 0 | 2h | 100%
Identify key roles and responsibilities for maintenance | Enterprise Architect | 0 | 2h | 100%
Identify key roles and responsibilities for maintenance | Functional Manager | 0 | 2h | 100%
Provide supporting documentation | Enterprise Architect | 0 | 2h | 100%
Provide supporting documentation | Functional Manager | 0 | 2h | 100%
Walk the team through the day to day of the maintenance | Enterprise Architect | 0 | 4h | 100%
Walk the team through the day to day of the maintenance | Functional Manager | 0 | 4h | 100%
Walk the team through the day to day of the maintenance | Technical Staff | 0 | 4h | 100%
Kickoff maintenance teamwork | Enterprise Architect | 0 | 2h | 100%
Kickoff maintenance teamwork | Functional Manager | 0 | 2h | 100%
Kickoff maintenance teamwork | Technical Staff | 0 | 2h | 100%
Reconfigure weighted DNS to GCP only | Developer | 0 | 2h | 100%
Decommission AWS resources | Developer | 0 | 2h | 100%